## Consultancy Services
Ministry/Department/Agency: National Orientation Agency
Budget Year: 2017
|  | Basic Data | [8 empty] | Preparation of Request For Proposals |  | Request for Expression of Interest |  | Shortlist |  | Consultants Proposals |  | Proposal Evaluation and Negotiation | [5 empty] | Contract Finalization |  |  |  | Contract Implementation - Consultancy |  |  |  | Action Party | Champion
Project Description |  | Package Number | Lot Number | Contract Type | Contract Amount | Procurement Method | Approval Threshold | Selection Method | Qualification | Review | Preparation and Submission by MDAs | MDA Approval | Advertisement | Lead-Time Before Shortlist | Submission Date | MDA Approval | Proposal Invitation/Submission Date | Closing/Opening Date | Submission of Technical Evaluation Report | MDA Approval | Openning of Financial Proposal | Submission of Evaluation Report - Technical/Financial | Negotiations | MDA Approval/No Objection Date | Certifiable Amount per Contract | FEC Approval | Date of Contract Offer | Date of Contract Signature | Mobilization/Advance Payment | Submission of Draft Report | Submission of Final Report | Final Cost | Name/Designation | Name/Designation
Normal duration of procurement Process | [8 empty] | If pre-qualification: add 2 weeks |  | 2 - 3 weeks | 2 weeks | 2.2 - 2 weeks | 3 weeks | 2 - 4 weeks | 2 weeks | 4 - 6 weeks |  | 2 weeks | 2 weeks | 2 weeks | 2 weeks | 2 weeks | 2 - 4 weeks |  | 2 weeks | 1 - 2 weeks | 2 weeks | 2 - 3 weeks
Plan vs Actual
Total Cost Plan
Total Cost Actual

## Goods
Ministry/Department/Agency: National Orientation Agency
Budget Year: 2017
|  | Basic Data | [8 empty] | Draft-Bid Documents |  | Specific Procurement Notice/Advert | Prequalification Evaluation |  | Bidding Period (Single Stage Tendering) |  | Bid Evaluation |  | Contract Finalization |  |  |  | Contract Implementation - Goods |  |  | Action Party | Champion
Project Description |  | Package Number | Lot Number | Contract Type | Contract Amount | Procurement Method | Approval Threshold | Selection Method | Qualification | Review | Preparation and Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification | Submission of Prequalification Evaluation Report | MDA Approval/No Objection Date | Bid Invitation Date | Bid Closing/Opening | Submission of Bid Evaluation Report | MDA Approval/BPP No Objection | Certifiable Amount per Contract | FEC Approval | Date of Contract Offer | Date of Contract Signature | Mobilization/Advance Payment | Arrival of Goods | Inspection/Final Acceptance | Name/Designation | Name/Designation
Normal duration of procurement Process | [8 empty] | If pre-qualification: add 2 weeks |  | 2 - 3 weeks | 2 weeks | 2 - 4 weeks | 2 weeks | 2 - 4 weeks | 4 - 6 weeks | 4 - 6 weeks | 2 - 3 weeks | 2 - 4 weeks |  | 2 weeks | 1 - 2 weeks | 2 weeks | 2 - 3 weeks |  | 2 weeks
Plan vs Actual
PURCHASE OF COMPUTER PRINTERS | Plan | NOA/PROC/CP/2017/01 | 1 | Sch of Del | 2100000 | NATIONAL SHOPPING | Chief Executive | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 10/07/17 - 24/07/17 | 25/07/17 - 08/08/17 | NA | NA | NA | 09/08/17 - 18/09/17 | 19/09/17 | 19/09/17 - 18/05/17 | 03/10/17 - 16/10/17 | 2100000 | NA | 17/10/17 - 31/10/17 | 02/11/17 - 16/11/17 | NA | 17/11/17 - 23/11/17 | 24/11/17 - 06/12/17 | REMI AFOLABI - [Designation: Director Procurement] | GARBA ABARI- [Designation: Director General]
Actual
PURCHASE OF PHOTOCOPYING MACHINES | Plan | NOA/PROC/PM/2017/02 | 2 | Sch of Del | 5000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 10/07/17 - 24/07/17 | 25/07/17 - 08/08/17 | NA | NA | NA | 09/08/17 - 18/09/17 | 19/09/17 | 19/09/17 - 18/05/17 | 03/10/17 - 16/10/17 | 5000000 | NA | 17/10/17 - 31/10/17 | 02/11/17 - 16/11/17 | NA | 17/11/17 - 23/11/17 | 24/11/17 - 06/12/17 | REMI AFOLABI - [Designation: Director Procurement] | GARBA ABARI- [Designation: Director General]
Actual
PURCHASE OF OFFICE FURNITURE AND FITTINGS | Plan | NOA/PROC/OF/2017/03 | 3 | Sch of Del | 20680000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 10/07/17 - 24/07/17 | 25/07/17 - 08/08/17 | NA | NA | NA | 09/08/17 - 18/09/17 | 19/09/17 | 19/09/17 - 18/05/17 | 03/10/17 - 16/10/17 | 20680000 | NA | 17/10/17 - 31/10/17 | 02/11/17 - 16/11/17 | NA | 17/11/17 - 23/11/17 | 24/11/17 - 06/12/17 | REMI AFOLABI - [Designation: Director Procurement] | GARBA ABARI- [Designation: Director General]
Actual
PURCHASE OF COMPUTERS | Plan | NOA/PROC/C/2017/04 | 4 | Sch of Del | 7350000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 10/07/17 - 24/07/17 | 25/07/17 - 08/08/17 | NA | NA | NA | 09/08/17 - 18/09/17 | 19/09/17 | 19/09/17 - 18/05/17 | 03/10/17 - 16/10/17 | 7350000 | NA | 17/10/17 - 31/10/17 | 02/11/17 - 16/11/17 | NA | 17/11/17 - 23/11/17 | 24/11/17 - 06/12/17 | REMI AFOLABI - [Designation: Director Procurement] | GARBA ABARI- [Designation: Director General]
Actual
PURCHASE OF POWER GENERATING | Plan | NOA/PROC/PGS/2017/05 | 5 | Sch of Del | 43000000 | NCB | Parastatals Tenders Board | LERB - LOWEST EVALUATED RESPONSIVE BID | POST-QUALIFICATION | POST REVIEW | 10/07/17 - 24/07/17 | 25/07/17 - 08/08/17 | NA | NA | NA | 09/08/17 - 18/09/17 | 19/09/17 | 19/09/17 - 18/05/17 | 03/10/17 - 16/10/17 | 43000000 | NA | 17/10/17 - 31/10/17 | 02/11/17 - 16/11/17 | NA | 17/11/17 - 23/11/17 | 24/11/17 - 06/12/17 | REMI AFOLABI - [Designation: Director Procurement] | GARBA ABARI- [Designation: Director General]
Actual
Total Cost Plan |  |  |  |  | 78130000 | [14 empty] | 78130000
Total Cost Actual

## Non-Consultancy Services
Ministry/Department/Agency: National Orientation Agency
Budget Year: 2017
|  | Basic Data | [8 empty] | Preparation of Request For Proposals |  | Request for Expression of Interest |  | Shortlist |  | Consultants Proposals |  | Proposal Evaluation and Negotiation | [5 empty] | Contract Finalization |  |  |  | Contract Implementation - Consultancy |  |  |  | Action Party | Champion
Project Description |  | Package Number | Lot Number | Contract Type | Contract Amount | Procurement Method | Approval Threshold | Selection Method | Qualification | Review | Preparation and Submission by MDAs | MDA Approval | Advertisement | Lead-Time Before Shortlist | Submission Date | MDA Approval | Proposal Invitation/Submission Date | Closing/Opening Date | Submission of Technical Evaluation Report | MDA Approval | Openning of Financial Proposal | Submission of Evaluation Report - Technical/Financial | Negotiations | MDA Approval/No Objection Date | Certifiable Amount per Contract | FEC Approval | Date of Contract Offer | Date of Contract Signature | Mobilization/Advance Payment | Submission of Draft Report | Submission of Final Report | Final Cost | Name/Designation | Name/Designation
Normal duration of procurement Process | [8 empty] | If pre-qualification: add 2 weeks |  | 2 - 3 weeks | 2 weeks | 2.2 - 2 weeks | 3 weeks | 2 - 4 weeks | 2 weeks | 4 - 6 weeks |  | 2 weeks | 2 weeks | 2 weeks | 2 weeks | 2 weeks | 2 - 4 weeks |  | 2 weeks | 1 - 2 weeks | 2 weeks | 2 - 3 weeks
Plan vs Actual
BUILDING A PEOPLE OF PEACE (COMMUNITY DIALOGUE FOR GENUINE RECONCILIATION AND HEALING OF MEMORIES) | Plan | NOA/HQ/PEMM/2017/01 | NA | NA | 30000000 | NA | Parastatals Tenders Board | NA | NA | POST-REVIEW | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 13/07/17 - 27/07/17 | NA | NA | NA | NA | NA | NA | NA | NA | RUTH OGUN -(Designation: Director: Public Education/Mass Mobilization) | GARBA ABARI- [Designation: Director General]
| Actual |  |  | NA |  | NA |  |  |  |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA |  | NA | NA | NA | NA | NA | NA | NA | NA
NATIONAL SECURITY AWARENESS SENSITISATION CAMPAIGN | Plan | NOA/HQ/DGO/2017/01 | NA | NA | 28611800 | NA | Parastatals Tenders Board | NA | NA | POST-REVIEW | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 13/07/17 - 27/07/17 | NA | NA | NA | NA | NA | NA | NA | NA | METE EDEKOBI-(Designation: Director, Special Duties & State Operations) | GARBA ABARI- [Designation: Director General]
| Actual |  | NA | NA |  | NA |  |  |  |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA |  | NA | NA | NA | NA | NA | NA | NA | NA
GRASSROOTS PUBLIC ENLIGHTENMENT SESSIONS IN THE WARDS AND LGAS ON THE MEANING, APPLICATION AND BENEFITS OF THE FREEDOM OF INFORMATION ACT, 2011. | Plan | NOA/HQ/PRS/2017/01 | NA | NA | 9422500 | NA | Parastatals Tenders Board | NA | NA | POST-REVIEW | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 13/07/17 - 27/07/17 | NA | NA | NA | NA | NA | NA | NA | NA | BONAT TAGWAI -(Designation: Director, Planning, Research & Strategies) | GARBA ABARI- [Designation: Director General]
| Actual |  | NA | NA |  | NA |  |  |  |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA |  | NA | NA | NA | NA | NA | NA | NA | NA
DO THE RIGHT THING: CAMPUS FOCUS PROGRAMME IN A TERTIARY INSTITUTION IN ONE STATE OF EACH OF THE SIX(6) GEO-POLITICAL ZONES IN NIGERIA | Plan | NOA/HQ/PRS/2017/02 | NA | NA | 23725600 | NA | Parastatals Tenders Board | NA | NA | POST-REVIEW | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 13/07/17 - 27/07/17 | NA | NA | NA | NA | NA | NA | NA | NA | BONAT TAGWAI -(Designation: Director, Planning, Research & Strategies) | GARBA ABARI- [Designation: Director General]
| Actual |  | NA | NA |  | NA |  |  |  |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA |  | NA | NA | NA | NA | NA | NA | NA | NA
CAMPAIGN AGAINST DESTRUCTION OF PUBLIC ASSETS | Plan | NOA/HQ/OBM/2017/01 | NA | NA | 10540000 | NA | Parastatals Tenders Board | NA | NA | POST-REVIEW | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 13/07/17 - 27/07/17 | NA | NA | NA | NA | NA | NA | NA | NA | MUSA CHANTU -(Designation: Director, Orientation & Behavioral Modification) | GARBA ABARI- [Designation: Director General]
| Actual |  | NA | NA |  | NA |  |  |  |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA |  | NA | NA | NA | NA | NA | NA | NA | NA
CHANGE BEGINS WITH ME - CAMPAIGN ON CONSERVATION AND PROTECTION OF PUBLIC ASSETS AND INFRASTRUCTURE | Plan | NOA/HQ/PEMM/2017/02 | NA | NA | 16184000 | NA | Parastatals Tenders Board | NA | NA | POST-REVIEW | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 13/07/17 - 27/07/17 | NA | NA | NA | NA | NA | NA | NA | NA | RUTH OGUN -(Designation: Director: Public Education/Mass Mobilization) | GARBA ABARI- [Designation: Director General]
| Actual |  | NA | NA |  | NA |  |  |  |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA |  | NA | NA | NA | NA | NA | NA | NA | NA
PROMOTING THE TENETS OF SOCIAL JUSTICE AND ALTERNATIVE DISPUTE RESOLUTION (ADR) | Plan | NOA/HQ/OBM/2017/03 | NA | NA | 31360000 | NA | Parastatals Tenders Board | NA | NA | POST-REVIEW | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 13/07/17 - 27/07/17 | NA | NA | NA | NA | NA | NA | NA | NA | MUSA CHANTU -(Designation: Director, Orientation & Behavioral Modification) | GARBA ABARI- [Designation: Director General]
| Actual |  | NA | NA |  | NA |  |  |  |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA |  | NA | NA | NA | NA | NA | NA | NA | NA
CHANGE BEGINS WITH ME - NATIONAL ACTION AGAINST DRUG ADDICTION, POLITICAL THUGGERY, KIDNAPPING, RADICALIZATION AND VIOLENT EXTREMISM | Plan | NOA/HQ/DGO/2017/02 | NA | NA | 15914000 | NA | Parastatals Tenders Board | NA | NA | POST-REVIEW | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 13/07/17 - 27/07/17 | NA | NA | NA | NA | NA | NA | NA | NA | MUSA CHANTU -(Designation: Director, Orientation & Behavioral Modification) | GARBA ABARI- [Designation: Director General]
| Actual |  | NA | NA |  | NA |  |  |  |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA |  | NA | NA | NA | NA | NA | NA | NA | NA
PEACE BUILDING COMMUNITY THEATRE (BUILDING A PEOPLE OF PEACE) | Plan | NOA/HQ/OBM/2017/03 | NA | NA | 20528800 | NA | Parastatals Tenders Board | NA | NA | POST-REVIEW | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 13/07/17 - 27/07/17 | NA | NA | NA | NA | NA | NA | NA | NA | METE EDEKOBI (Designation: Director, Special Duties & State Operations) | GARBA ABARI- [Designation: Director General]
Actual
Total Cost Plan |  |  |  |  | 186286700
Total Cost Actual

## Works
Ministry/Department/Agency: National Orientation Agency
Budget Year: 2017
|  | Basic Data | [8 empty] | Draft-Bid Documents |  | Specific Procurement Notice/Advert | Prequalification Evaluation |  | Two Stage Tendering |  | Bidding Period (Single Stage Tendering) |  | Bid Evaluation |  | Contract Finalization |  |  |  | Contract Implementation - Works |  |  |  | Action Party | Champion
Project Description |  | Package Number | Lot Number | Contract Type | Contract Amount | Procurement Method | Approval Threshold | Selection Method | Qualification | Review | Preparation and Submission by MDAs | MDA Approval | Advertisement for Pre-Qualification | Submission of Prequalification Evaluation Report | MDA Approval/No Objection Date | First Stage Bidding | Second Stage Bidding - Technical/Financial | Bid Invitation Date | Bid Closing/Opening | Submission of Bid Evaluation Report | MDA Approval/BPP No Objection | Certifiable Amount per Contract | FEC Approval | Date of Contract Offer | Date of Contract Signature | Mobilization/Advance Payment | Substantial Completion | Final Acceptance | Final Cost | Name/Designation | Name/Designation
Normal duration of procurement Process | [8 empty] | If pre-qualification: add 2 weeks |  | 2 - 3 weeks | 2 weeks | 2 - 4 weeks | 2 weeks | 2 - 4 weeks | 2 - 3 weeks | 4 - 6 weeks | 4 - 6 weeks | 4 - 6 weeks | 2 - 3 weeks | 2 - 4 weeks |  | 2 weeks | 1 - 2 weeks | 2 weeks | 2 - 3 weeks |  | 134.4 weeks
Plan vs Actual
CONSTRUCTION OF OFFICE BUILDING (COMPLETION OF ON-GOING PROJECT IN KOGI, NASARAWA & OSUN STATES) | Plan | NOA/RN/01/2012 | ON-GOING | ON-GOING | 134000000 | ON-GOING | Parastatals Tenders Board | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 134000000 | NA | NA | NA | NA | NA | NA | NA | REMI AFOLABI - [Designation: Director Procurement] | GARBA ABARI- [Designation: Director General]
Actual
PURCHASE OF OFFICE BUILDING IN EKITI | Plan | NOA/PROC/OBE/2017/01 | NA | Sch of Del | 16047661 | NCB | Parastatals Tenders Board | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 16047661 | NA | NA | NA | NA | NA | NA | NA | REMI AFOLABI - [Designation: Director Procurement] | GARBA ABARI- [Designation: Director General]
Actual
Total Cost Plan |  |  |  |  | 150047661
Total Cost Actual